## Gantt Chart
Task | Start Date | End Date | Duration (days)
Define objectives and scope | 2025-01-01 | 2025-01-08 | 7
Research sustainable materials | 2025-01-08 | 2025-01-15 | 7
Source materials and smart textiles | 2025-01-22 | 2025-01-29 | 7
Ideation and initial sketches | 2025-01-22 | 2025-01-29 | 7
Create first prototype design | 2025-01-29 | 2025-02-12 | 14
Build and test basic prototypes | 2025-02-12 | 2025-02-19 | 7
Gather feedback on prototypes | 2025-02-19 | 2025-02-26 | 7
Improve prototype design based on feedback | 2025-01-29 | 2025-02-12 | 14
Test durability and usability | 2025-02-12 | 2025-03-05 | 21
Develop final reusable pad design | 2025-02-19 | 2025-02-26 | 7
Create video and visuals for presentation | 2025-02-26 | 2025-03-05 | 7
Prepare project documentation | 2025-03-05 | 2025-03-12 | 7
Present final project | 2025-03-19 | 2025-03-26 | 7