## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Gratitude Loom
PROJECT MANAGER |  | Pattaraporn (Porpla) Kittisapkjon
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO | [20 empty] | PHASE THREE | [20 empty] | PHASE FOUR
[6 empty] | EXPLORATION & FRAMING | [20 empty] | TRANSLATION INTO SYSTEM & LOGIC (DESIGN) | [20 empty] | PROTOTYPING & TESTING | [20 empty] | DOCUMENTATION & PRESENTATION
[6 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
[6 empty] | 01/12 - 01/18 | [6 empty] | 01/19 - 01/25 | [6 empty] | 01/26 - 02/01 | [6 empty] | 02/02 - 02/08 | [6 empty] | **02/09 - 02/15** | [6 empty] | 02/16 - 02/22 | [6 empty] | 02/23 - 03/01 | [6 empty] | 03/02 - 03/08 | [6 empty] | 03/09 - 03/15 | [6 empty] | 03/16 - 03/22 | [6 empty] | 03/23 - 03/29 | [6 empty] | **03/30 - 04/02**
[6 empty] | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU | M | T | W | R | F | SA | SU
1 | Project Planning and Definition
1.1 | Create Gantt Chart | 2026-01-12 | 2026-01-18 | 6 | 100% | bar: 01/12 - 01/18 M to 01/12 - 01/18 SU
| Create Bill of Materials | 2026-01-12 | 2026-01-18 | 6 | 100% | bar: 01/12 - 01/18 M to 01/12 - 01/18 SU
1.1 | Define Project | 2026-01-12 | 2026-01-18 | 6 | 100%
1.1.1 | Define System Components | 2026-01-19 | 2026-01-25 | 6 | 100%
1.2 | Define System Relationships | 2026-01-19 | 2026-01-25 | 6 | 100%
1.2.1 | System Diagram | 2026-01-19 | 2026-01-25 | 6 | 100%
1.3 | Define System Boundaries | 2026-01-19 | 2026-01-25 | 6 | 100%
1.4 | Moodboard | 2026-01-19 | 2026-01-25 | 6 | 100%
2 | Research and References
2.1 | Conceptual Foundations | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.2 | Ritual, Presence, and Memory | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2,3 | Existing Gratitude Practice | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.4 | Craft as Knowledge System | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.5 | Anatomy of the Loom | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.6 | Jacquard Loom / Programmable Machine | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.7 | Woven Pattern Logic | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.8 | Basic Weave Structure and Pattern Grammar | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.9 | Design Constraints for Weavable Pattern Logic | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.1 | Sequence of Weaving Process | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.11 | Ref. Human-Machine Collaboration | 2026-01-26 | 2026-02-02 | 6 | 100% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.12 | Ref. Opensource Loom | 2026-01-26 | 2026-02-02 | 6 | 50% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.13 | Ref. Computer-controlled looms | 2026-01-26 | 2026-02-02 | 6 | 50% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.14 | Ref.Computational / Algorithmic Weaving & Textile Systems | 2026-01-26 | 2026-02-02 | 6 | 0% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.15 | Ref. Voice & Sound as Input Interfaces | 2026-01-26 | 2026-02-02 | 6 | 0% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
2.16 | Ref. Ritual, Mindfulness & Embodied Interaction | 2026-01-26 | 2026-02-02 | 6 | 0% | bar: 01/26 - 02/01 M to 01/26 - 02/01 SU
3 | Design
3.1 | Ritual and Interaction Flow Design | 2026-02-02 | 2026-02-10 | 8 | 100% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
3.1.1 | Ritual Interaction Logic Table | 2026-02-02 | 2026-02-10 | 8 | 100% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
3.2 | Pattern Logic | 2026-02-02 | 2026-02-10 | 8 | 50% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
3.2.1 | Pattern Logic Chart | 2026-02-02 | 2026-02-10 | 8 | 25% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
3.3 | System Design | 2026-02-02 | 2026-02-10 | 8 | 100% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
| System Diagram | 2026-02-02 | 2026-02-10 | 8 | 100% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
3.3.1 | Electronic Design | 2026-02-02 | 2026-02-10 | 8 | 50% | bar: 01/26 - 02/01 T; 02/02 - 02/08 M to 02/16 - 02/22 SU
| Electronic Diagram | 2026-02-02 | 2026-02-10 | 8 | 0% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
3.3 | Loom Design | 2026-02-02 | 2026-02-10 | 8 | 50% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
3.3.1 | Component Drawing | 2026-02-02 | 2026-02-10 | 8 | 0% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
3.3.2 | Assembly Drawing | 2026-02-02 | 2026-02-10 | 8 | 0% | bar: 02/02 - 02/08 M to 02/16 - 02/22 SU
Midterm Review (MR)
MR 1 | Updated Presentation Slides | 2026-02-09 | 2026-02-10 | 1 | 0 % | bar: 01/12 - 01/18 M to **03/30 - 04/02** SU
MR 1.1 | Text | 2026-02-09 | 2026-02-10 | 1 | 0 % | bar: 01/12 - 01/18 M to **03/30 - 04/02** SU
MR 1.2 | Drawing | 2026-02-09 | 2026-02-10 | 1 | 0 % | bar: 01/12 - 01/18 M to **03/30 - 04/02** SU
MR 1.3 | Diagram | 2026-02-09 | 2026-02-10 | 1 | 0 % | bar: 01/12 - 01/18 M to **03/30 - 04/02** SU
MR 1.4 | Image | 2026-02-09 | 2026-02-10 | 1 | 0 % | bar: 01/12 - 01/18 M to **03/30 - 04/02** SU
4 | Prototyping & Testing
4.1 | Core System (Solo Prototype) | 2026-02-16 | 2026-03-01 | 15 | 0% | bar: **02/09 - 02/15** M to 02/16 - 02/22 SU
4.1.2 | Beating IMU Sensor | 2026-02-16 | 2026-03-01 | 15 | 0% | bar: **02/09 - 02/15** M to 02/16 - 02/22 SU
4.1.3 | Shuttle Sensor |  |  |  | 50% | bar: **02/09 - 02/15** M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.4 | Beating Hall sensor | bar: **02/09 - 02/15** M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.5 | ESP32 Sending Data | bar: **02/09 - 02/15** M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.6 | Setting up warp for prototyping |  |  |  | 100% | bar: **02/09 - 02/15** M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.7 | Baseline Calibration Working | 2026-02-16 | 2026-03-01 | 15 | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.8 | State machine Working | 2026-02-16 | 2026-03-01 | 15 | 0% | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.9 | Voice Speaking on Transitions | 2026-02-23 | 2026-03-05 | 12 | 0% | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.10 | Tune Tresholds | 2026-02-23 | 2026-03-05 | 12 | 0% | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.11 | Weave test sample showing 3 states | 2026-02-23 | 2026-03-05 | 12 | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.12 | Data logged | 2026-02-23 | 2026-03-05 | 12 | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.13 | System runs for 10 minutes without crashing | 2026-02-23 | 2026-03-05 | 12 | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.14 | Setting up warp for final documentation | 2026-02-24 | 2026-03-06 | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.15 | FIlm weaving close-ups | 2026-02-25 | 2026-03-07 | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.1.16 | Photograph Textile | 2026-02-23 | 2026-03-05 | 12 | bar: 02/23 - 03/01 M to 02/23 - 03/01 F; 02/23 - 03/01 SU to 03/02 - 03/08 SU
4.2 | Collective Mode | 2026-03-09 | 2026-03-15 | 6 | 0% | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
4.2.1 | Baseline Calibration Working | 2026-02-16 | 2026-03-15 | 29 | 0% | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
4.2.2 | Inheritance model implemented | 2026-02-16 | 2026-03-15 | 29 | 0% | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
Capture State transitions on screen | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
4.2.3 | 1 test textile with 3 people | 2026-02-16 | 2026-03-15 | 29 | 0% | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
Data logged | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
Clean Footage | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
4.2.4 | Stable System | 2026-02-16 | 2026-03-15 | 29 | 0% | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
5 | Production
5.1 | Develope Storyboard | 2026-03-09 | 2026-03-15 | bar: 03/02 - 03/08 M to 03/09 - 03/15 SU
5.2 | Video Documentation | 2026-03-16 | 2026-03-22 | [86 empty] | 100% | bar: 03/16 - 03/22 M to 03/23 - 03/29 SU
5.3 | Video Editing | 2026-03-16 | 2026-03-29 | bar: 03/16 - 03/22 M to 03/23 - 03/29 SU
5.4 | Build Slides | 2026-03-16 | 2026-03-29 | bar: 03/16 - 03/22 M to 03/23 - 03/29 SU
5.5 | Design Booklet | 2026-03-16 | 2026-03-29 | bar: 03/16 - 03/22 M to 03/23 - 03/29 SU
5.6 | Write Reflection | 2026-03-16 | 2026-03-29 | bar: 03/16 - 03/22 M to 03/23 - 03/29 SU
5.7 | Practice Presentation | 2026-03-16 | 2026-03-29 | 13 | 0% | bar: 03/16 - 03/22 M to 03/23 - 03/29 SU
7 | Final Review (FR)
7.1 | Final Video | 2026-03-23 | 2026-03-29 | 6 | 0 % | bar: 01/12 - 01/18 M to **03/30 - 04/02** SU
7.2 | Final Presentation Slide | 2026-03-23 | 2026-03-29 | 6 | 0 % | bar: 01/12 - 01/18 M to **03/30 - 04/02** SU